TaskChain

Implementation Plan

Version 1.0 | Phased Delivery Roadmap

# 1. Executive Summary

This implementation plan outlines a 12-week phased approach to deliver TaskChain MVP. The plan prioritizes early value delivery through a working similarity engine, followed by prediction capabilities and feedback loops.

## 1.1 Timeline Overview

| Phase | Duration | Focus | Deliverable |
| --- | --- | --- | --- |
| Phase 1: Foundation | Weeks 1-3 | Core infrastructure & data model | Working API with basic CRUD |
| Phase 2: Intelligence | Weeks 4-6 | Similarity engine & search | Auto-surfacing of related tasks |
| Phase 3: Predictions | Weeks 7-9 | Timeline & risk predictions | Full prediction display |
| Phase 4: Workflows | Weeks 10-11 | Acknowledgment & review flows | Complete user journeys |
| Phase 5: Polish | Week 12 | Testing, fixes, deployment | Production-ready MVP |

## 1.2 Team Requirements

- 1 Backend Developer (Go) - Full time

- 1 Frontend Developer (React) - Full time from Week 3

- 0.5 DevOps/Platform - Setup and support

- Product Owner - Part time for decisions and testing

# 2. Phase 1: Foundation (Weeks 1-3)

## 2.1 Objectives

- Establish project structure and development environment

- Implement core data model with PostgreSQL + pgvector

- Build basic task CRUD API

- Set up CI/CD pipeline

## 2.2 Week 1: Project Setup

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Initialize Go project with Fiber | Backend | 4 | None |
| Set up PostgreSQL with pgvector extension | DevOps | 4 | None |
| Create database migrations system | Backend | 4 | PostgreSQL ready |
| Implement core entity models | Backend | 8 | Migrations ready |
| Set up development Docker Compose | DevOps | 4 | None |
| Configure linting, testing framework | Backend | 4 | Project initialized |

### Deliverables

- Running local development environment

- Database with core tables created

- Passing CI build with linting

## 2.3 Week 2: Task API

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement task repository layer | Backend | 8 | Models ready |
| Build POST /tasks endpoint | Backend | 4 | Repository ready |
| Build GET /tasks/:id endpoint | Backend | 2 | Repository ready |
| Build PUT /tasks/:id endpoint | Backend | 3 | Repository ready |
| Build GET /tasks (list with filters) | Backend | 6 | Repository ready |
| Add request validation | Backend | 4 | Endpoints ready |
| Write unit tests for task service | Backend | 6 | Service ready |
| Set up API documentation (Swagger) | Backend | 3 | Endpoints ready |

### Deliverables

- Fully functional task CRUD API

- Swagger documentation

- >80% test coverage on task service

## 2.4 Week 3: Supporting Entities & Auth

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement task_links repository & endpoints | Backend | 6 | Task API ready |
| Implement task_justifications endpoints | Backend | 4 | Task API ready |
| Implement task_blockers endpoints | Backend | 4 | Task API ready |
| Integrate with existing SSO | Backend | 8 | None |
| Add authorization middleware | Backend | 4 | SSO integrated |
| Initialize React project | Frontend | 4 | None |
| Set up frontend build pipeline | DevOps | 4 | React project ready |

### Deliverables

- Complete API for all core entities

- Working authentication flow

- Frontend project scaffold

## 2.5 Phase 1 Exit Criteria

- All core tables created with proper indexes

- Task CRUD operations working end-to-end

- Authentication integrated and tested

- CI/CD pipeline deploying to staging

- API documentation complete

# 3. Phase 2: Intelligence (Weeks 4-6)

## 3.1 Objectives

- Implement embedding generation for tasks

- Build similarity search functionality

- Create auto-surfacing of related tasks on creation

- Build basic task management UI

## 3.2 Week 4: Embedding Infrastructure

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Set up sentence-transformers service | Backend | 6 | None |
| Implement embedding generation on task create | Backend | 4 | Service ready |
| Build async embedding update worker | Backend | 6 | Service ready |
| Create pgvector similarity search queries | Backend | 6 | Embeddings stored |
| Build /tasks/:id/similar endpoint | Backend | 4 | Search queries ready |
| Add embedding index management | Backend | 4 | Queries working |
| Build task list UI component | Frontend | 8 | API ready |

## 3.3 Week 5: Similarity Engine

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement boost factors for similarity ranking | Backend | 6 | Basic search working |
| Add outcome weighting (failures surfaced first) | Backend | 4 | Boost factors ready |
| Integrate similarity search into task creation | Backend | 4 | Engine complete |
| Build task detail UI with similar tasks panel | Frontend | 8 | API ready |
| Build task creation form | Frontend | 8 | API ready |
| Performance optimization for search | Backend | 4 | UI integrated |
| Write integration tests for similarity | Backend | 4 | Engine stable |

## 3.4 Week 6: Linking & Justification UI

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Build task linking UI component | Frontend | 6 | Similar tasks displayed |
| Build justification form UI | Frontend | 6 | Linking UI ready |
| Implement link type selection | Frontend | 4 | Linking UI ready |
| Add validation for link-or-justify requirement | Backend | 4 | Endpoints ready |
| Build task history/context chain view | Frontend | 8 | Links working |
| End-to-end testing of creation flow | QA/Team | 6 | All components ready |
| Cold start: Import sample data | Backend | 4 | System working |

## 3.5 Phase 2 Exit Criteria

- Similarity search returning relevant results (<2s latency)

- Task creation surfaces related tasks automatically

- Users can link tasks or submit justifications

- Basic UI functional for task management

- Sample data imported for testing

# 4. Phase 3: Predictions (Weeks 7-9)

## 4.1 Objectives

- Implement timeline prediction algorithm

- Build blocker risk prediction

- Create planning quality assessment

- Display predictions in UI

## 4.2 Week 7: Timeline Prediction

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement weighted average timeline calculation | Backend | 6 | Similarity engine ready |
| Build confidence interval calculation | Backend | 4 | Basic prediction ready |
| Add adjustment factors (dependencies, capacity) | Backend | 4 | Confidence ready |
| Create predictions endpoint | Backend | 4 | Algorithm complete |
| Build prediction display component | Frontend | 6 | Endpoint ready |
| Add prediction to task creation response | Backend | 2 | Component ready |
| Write tests for prediction accuracy | Backend | 4 | Algorithm stable |

## 4.3 Week 8: Risk & Quality Assessment

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement blocker probability calculation | Backend | 6 | Blocker data available |
| Build blocker risk display component | Frontend | 6 | Endpoint ready |
| Implement planning quality scoring | Backend | 6 | Task data complete |
| Build quality assessment UI with suggestions | Frontend | 6 | Scoring ready |
| Add historical blocker examples to response | Backend | 4 | Risk calc ready |
| Integration testing of prediction suite | QA/Team | 4 | All predictions working |

## 4.4 Week 9: Prediction Refinement

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Tune similarity thresholds based on testing | Backend | 6 | Data available |
| Optimize prediction queries | Backend | 4 | Baseline established |
| Build prediction explanation tooltips | Frontend | 4 | Predictions displayed |
| Add comparison with user estimate | Frontend | 4 | Predictions ready |
| Create prediction accuracy tracking | Backend | 6 | Predictions complete |
| User testing session #1 | Team | 4 | UI stable |
| Bug fixes from testing | Both | 8 | Testing complete |

## 4.5 Phase 3 Exit Criteria

- Timeline predictions displayed with confidence intervals

- Blocker risks shown with probability and examples

- Planning quality score calculated and explained

- Predictions integrated into task creation flow

- Initial accuracy baseline established

# 5. Phase 4: Workflows (Weeks 10-11)

## 5.1 Objectives

- Implement mandatory acknowledgment flow

- Build task completion review form

- Create feedback capture mechanism

- Build basic analytics dashboard

## 5.2 Week 10: Acknowledgment & Completion

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Implement acknowledgment state machine | Backend | 4 | Task status complete |
| Build acknowledgment UI with options | Frontend | 6 | State machine ready |
| Add enforcement: no start without acknowledgment | Backend | 4 | UI ready |
| Build completion review form | Frontend | 8 | API ready |
| Implement review submission endpoint | Backend | 4 | Form ready |
| Add blocker logging during task execution | Frontend | 6 | Blocker API ready |
| Build task timeline view (start to complete) | Frontend | 4 | Data available |

## 5.3 Week 11: Analytics & Feedback

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| Build prediction accuracy analytics | Backend | 6 | Review data available |
| Create blocker pattern analysis queries | Backend | 4 | Blocker data available |
| Build timeline accuracy analysis | Backend | 4 | Completion data available |
| Create analytics dashboard UI | Frontend | 8 | Endpoints ready |
| Implement feedback model updates (batch job) | Backend | 6 | Analytics ready |
| Add linking rate metrics | Backend | 2 | Link data available |
| User testing session #2 | Team | 4 | Workflows complete |

## 5.4 Phase 4 Exit Criteria

- Complete task lifecycle working: create → acknowledge → start → complete → review

- Users cannot bypass acknowledgment step

- Completion reviews captured for all closed tasks

- Basic analytics dashboard showing key metrics

- Feedback loop updating prediction models

# 6. Phase 5: Polish (Week 12)

## 6.1 Objectives

- Complete end-to-end testing

- Fix critical bugs

- Performance optimization

- Production deployment

## 6.2 Week 12: Launch Preparation

### Tasks

| Task | Owner | Est Hours | Dependencies |
| --- | --- | --- | --- |
| End-to-end regression testing | QA/Team | 8 | All features complete |
| Critical bug fixes | Both | 12 | Testing complete |
| Performance profiling and optimization | Backend | 6 | Stable build |
| Security review | Backend/DevOps | 4 | Code freeze |
| Production infrastructure setup | DevOps | 6 | Config finalized |
| Data migration for pilot team | Backend | 4 | Prod ready |
| Documentation and training materials | Team | 6 | Features stable |
| Soft launch to pilot team | Team | 2 | All above complete |

## 6.3 Launch Criteria

- All P0 features working without critical bugs

- Response times meeting performance targets

- Security review passed

- Pilot team onboarded and trained

- Monitoring and alerting configured

- Rollback plan documented

# 7. Risk Management

## 7.1 Technical Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Embedding quality insufficient | Medium | High | Test early with real data, have fallback to keyword search |
| Performance issues at scale | Low | Medium | Load test in Week 9, optimize before launch |
| SSO integration delays | Medium | Medium | Start in Week 1, have basic auth fallback |
| pgvector scaling issues | Low | High | Monitor closely, plan for dedicated vector DB if needed |

## 7.2 Schedule Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Frontend developer unavailable Week 3 | Low | High | Backend can build basic UI, prioritize API completeness |
| Scope creep from stakeholders | High | Medium | Strict change control, defer to post-MVP |
| Testing finds major issues | Medium | Medium | Buffer time in Week 12, can extend 1 week if needed |

# 8. Post-Launch Success Metrics

## 8.1 Week 1-4 After Launch

| Metric | Target | Measurement Method |
| --- | --- | --- |
| User adoption | >80% of pilot team active | Daily active users |
| Task creation with context | >70% linked or justified | Database query |
| Acknowledgment compliance | 100% | No tasks started without ack |
| System uptime | >99% | Monitoring alerts |

## 8.2 Month 2-3 After Launch

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Prediction accuracy | >60% | Actual within predicted range |
| Repeated failure reduction | >30% | Compare to pre-launch baseline |
| User satisfaction | >3.5/5 | Survey + feedback ratings |
| Review completion | >90% | Completed tasks with reviews |

# 9. Appendix

## 9.1 Key Milestones

| Date | Milestone | Deliverable |
| --- | --- | --- |
| End of Week 3 | Foundation Complete | Working API with auth |
| End of Week 6 | Intelligence Complete | Similarity search live |
| End of Week 9 | Predictions Complete | Full prediction suite |
| End of Week 11 | Workflows Complete | Complete user journey |
| End of Week 12 | MVP Launch | Production deployment |

## 9.2 Dependencies

- PostgreSQL 16 with pgvector extension availability

- Kubernetes cluster access for deployment

- SSO/OIDC provider credentials

- Pilot team commitment (5-10 users)

- Sample historical task data for cold start

## 9.3 Communication Plan

- Daily standups during development

- Weekly stakeholder updates

- Demo at end of each phase

- Dedicated Slack channel for pilot feedback